# Nexus Customer Portal – Monthly Project Report

Reporting Period: February 2026

Report Date: March 3, 2026

Prepared by: Project Management Office

Version: 1.0 – Final

## Executive Summary

February 2026 was a month of strong foundational progress on the Nexus Customer Portal project. All five delivery streams met their February commitments, and the project is 2% ahead of the baseline plan heading into March. Overall project completion stands at 42% against a plan of 40%.

The project is rated AMBER overall. While delivery is on track, three emerging risks require proactive management in March: the Salesforce CRM sandbox access request (now 2 weeks outstanding), the DBA team schema approval process (first submission pending), and a shared infrastructure environment that is creating friction across multiple streams.

Key highlights for February:

Authentication and SSO flows (Azure AD, MFA) fully implemented and passed security review

Integration architecture approved by Architecture Review Board (February 28)

Design system v2.0 delivered; component library work underway in Frontend Dev

Round 1 usability testing completed: 8 participants, SUS score 73/100 (Good)

Azure Service Bus integration infrastructure provisioned and operational

Key concerns entering March:

Salesforce sandbox provisioning has not started — CRM integration work begins in March

DBA team capacity may bottleneck database schema approvals (first submission pending)

Dedicated staging environment not provisioned — Infrastructure team 2 weeks behind schedule

CI/CD test pipeline configuration not yet scheduled by DevOps team

## Project Management

Overall Status: AMBER

Budget Status: GREEN – 91% of February budget utilized; on track YTD

Schedule Status: AMBER – 2% ahead overall, but critical path items emerging at risk for Q2

Resource Status: GREEN – all planned team members onboarded

### Milestone Tracker

| Milestone | Target Date | Status | Notes |
| --- | --- | --- | --- |
| Architecture Review Board Approval | January 30, 2026 | ✅ COMPLETE | Approved unanimously |
| Authentication Module Complete | February 14, 2026 | ✅ COMPLETE | Passed security review Feb 18 |
| Design System v2.0 Delivered | February 21, 2026 | ✅ COMPLETE | Published to Figma library |
| Integration Architecture Approved | February 28, 2026 | ✅ COMPLETE | ARB sign-off received |
| Staging Environment Provisioned | February 28, 2026 | 🔴 MISSED | Infrastructure team delay; rescheduled to March 21 |
| CRM Integration Development Start | March 3, 2026 | 🟡 AT RISK | Salesforce sandbox access not yet received |
| Customer Dashboard API Complete | March 7, 2026 | 🟡 AT RISK | DBA schema approval pending |
| Design System v2.1 Sign-off | March 10, 2026 | 🟡 AT RISK | Marketing brand guidelines not finalized |

### Open Decisions (required in March)

| Decision | Owner | Due Date | Impact if Delayed |
| --- | --- | --- | --- |
| IE11 browser support (deprecate or support) | IT Director | March 14 | 3 weeks of additional frontend dev if support required |
| Real-time vs. batch CRM sync approach | Architecture / Sponsor | March 7 | Blocks Integrations stream architecture finalization |
| DBA review SLA establishment | PMO / DBA Manager | March 7 | Schema approvals becoming bottleneck for Backend stream |
| Accessibility audit budget approval ($8,500) | Finance / Sponsor | March 21 | Blocks WCAG audit before UAT |

### Project-Level Risks

| # | Risk | Status | Owner |
| --- | --- | --- | --- |
| 1 | Salesforce access delay threatens CRM integration milestone (May 2) | 🔴 Escalating | David Reyes / Sponsor |
| 2 | Shared infrastructure environment causing multi-stream productivity loss | 🟡 Active | PMO / Infrastructure |
| 3 | No formal API contract management process between Backend and Frontend | 🟡 Active | Priya Nair / Marcus Okonkwo |
| 4 | DBA team approval capacity may become critical path bottleneck | 🟡 Watch | Priya Nair / PMO |
| 5 | Test automation not integrated into CI/CD, slowing quality feedback loop | 🟡 Active | Aisha Williams / DevOps |

## UX Stream – February 2026

Status: GREEN | Sprint Velocity: 41 / 42 story points (98%)

### Completed This Month

Design system v2.0 finalized and published to Figma shared library (colors, typography, spacing tokens, 28 base components)

Authentication screens (login, Azure AD SSO, MFA setup) – design handoff completed and accepted by Frontend Dev

User profile management screens – design handoff completed

Round 1 usability testing: 8 internal participants; SUS score 73/100; key finding: navigation structure rated highly, form validation messaging needs improvement

Design token definitions exported for use in the Frontend component library

### Top 5 Risks

Brand guideline finalization (due March 15) may require retroactive design updates to v2.0 components

Mobile design complexity for account management screens is higher than estimated (+2 story points per screen)

Product Owner prototype review capacity is insufficient for sprint cadence (identified in retrospective)

Accessibility audit not yet scheduled; WCAG 2.1 AA certification required before UAT

Design-to-Dev handoff process lacks formal acceptance criteria checklist

### Blockers

None in February.

### Leadership Asks

None in February.

### Delayed Tasks

Mobile account management wireframes were started but not completed in February (moved to March Sprint 11 — 1 sprint slip, not on critical path).

### Summary

An excellent delivery month for UX. The design system is the cornerstone deliverable that enables frontend development scale in Q2. Round 1 usability testing results are encouraging, with the navigation approach validated. The primary risk heading into March is the dependency on brand guideline finalization from Marketing.

## Frontend Dev Stream – February 2026

Status: GREEN | Sprint Velocity: 40 / 42 story points (95%)

### Completed This Month

React 18 / TypeScript project architecture, build pipeline (Vite), and coding standards finalized

Authentication flows fully implemented: email/password login, Azure AD SSO integration, MFA with authenticator app

User profile management screens implemented and connected to backend APIs

Design system component library: 35 components implemented (buttons, forms, modals, navigation, data display)

Unit test coverage increased from 45% to 62%

react-query v5 package approval request submitted to IT Security (February 20)

### Top 5 Risks

Backend API availability for customer dashboard module (dependency starting Sprint 10)

JavaScript bundle size growing; performance optimisation needed before load testing phase

Pending react-query v5 approval adding workaround development overhead

Safari 16 CSS Grid compatibility issues identified in early cross-browser testing

API contract changes from Backend team causing frontend service layer rework (1 occurrence in February)

### Blockers

None blocking in February. react-query v5 approval request submitted proactively.

### Leadership Asks

Approve `react-query v5` package – submitted to IT Security February 20 for standard review.

### Delayed Tasks

None – all February commitments met.

### Summary

Productive delivery month. Authentication and profile features delivered on time and to quality standards. The component library foundation is strong. Proactively submitted the react-query package approval to avoid a March blocker.

## Backend Dev Stream – February 2026

Status: GREEN | Sprint Velocity: 39 / 42 story points (93%)

### Completed This Month

Authentication and Authorization API: JWT token issuance, OAuth 2.0 flows, refresh token rotation, Azure AD integration

User Profile CRUD API: full implementation with validation and audit logging

Document Storage Service: Azure Blob Storage integration with virus scan, SAS URL generation

Notification Service: email dispatch (SendGrid) and push notification support

API versioning strategy implemented across all endpoints

Swagger / OpenAPI documentation: 8 endpoints fully documented

Database schema v3.1 submitted to DBA team for approval (February 25)

### Top 5 Risks

DBA team capacity may become a bottleneck — first schema approval request submitted; SLA unknown

Dedicated staging environment not provisioned (Infrastructure team delay)

Payment gateway integration complexity higher than initial T-shirt sizing estimate

Legacy CRM data quality analysis reveals 23% quality issues (duplicates, missing mandatory fields)

Azure Key Vault migration is a pre-go-live requirement not yet scheduled

### Blockers

Database schema v3.1 approval submitted February 25 to DBA team — awaiting response.

### Leadership Asks

Formal request for an additional Q2 developer resource to be submitted in March once payment gateway complexity is fully assessed.

### Delayed Tasks

None – all February commitments met.

### Summary

Solid delivery month. All four core service APIs delivered on schedule. The DBA approval process has been identified as a risk for March; a follow-up SLA request will be submitted in early March. The data quality issue in legacy CRM data will require a dedicated remediation sprint, which has been flagged to the Project Manager.

## Integrations Stream – February 2026

Status: GREEN | Sprint Velocity: 38 / 42 story points (90%)

### Completed This Month

Integration architecture design document finalized (event-driven, Azure Service Bus, REST adapters)

Architecture Review Board approval received (February 28) — all architectural decisions ratified

Azure Service Bus infrastructure provisioned, topics/subscriptions configured

Integration framework implemented: base adapter, circuit breaker (Polly), retry logic, dead-letter queue handling

Stripe payment integration: sandbox account configured, basic payment intent creation 30% implemented

Data transformation utilities for Salesforce CRM contact/account field mapping

### Top 5 Risks

Salesforce sandbox provisioning requested (February 14) — not yet processed (1 week outstanding at end of February)

SAP ERP API documentation quality concern raised by team — may be incomplete for key endpoints

Stripe API rate limits in sandbox (100 req/s) may be insufficient for load testing

Data synchronisation conflict resolution strategy requires architectural decision (linked to real-time vs batch decision)

Vendor API stability monitoring needed; added Stripe changelog watchlist

### Blockers

Salesforce CRM sandbox access request submitted February 14 — provisioning not yet started as of February 28 (2 weeks outstanding).

### Leadership Asks

Pending decision: Real-time vs. batch CRM sync approach (must be resolved before CRM integration architecture is finalized)

Potential escalation needed if Salesforce sandbox access is not received by March 7

### Delayed Tasks

None — February commitments met. Salesforce CRM development work was not scheduled to begin until March Sprint 10.

### Summary

A strong architecture month. The integration framework and infrastructure will enable rapid integration development once the Salesforce environment is available. The ARB approval provides confidence in the technical direction. Salesforce access is the primary risk heading into March, when CRM integration development is scheduled to begin.

## Testing Stream – February 2026

Status: GREEN | Sprint Velocity: 37 / 42 story points (88%)

### Completed This Month

Test strategy document finalized and signed off by Project Manager

Testing toolchain configured: Playwright 1.42 (E2E), NUnit (unit/integration), k6 (performance), Postman/Newman (API)

Authentication module: full unit, integration, and E2E test coverage complete

User Profile module: unit and integration test coverage complete

Defect tracking process configured in Azure DevOps; defect triage cadence established (daily standby triage, Monday formal triage)

Risk-based testing prioritisation matrix created and shared with project team

### Top 5 Risks

Late feature deliveries from other streams will compress available testing time in Q2

Shared development environment disruptions (Dev team resets and deployments overwriting test data)

CI/CD automated test pipeline configuration not yet in Azure DevOps backlog (submitted request)

E2E test flakiness already emerging at 7% in authentication flows — needs stabilisation tooling

Performance testing requires a dedicated execution environment not yet available

### Blockers

CI/CD pipeline configuration task submitted to DevOps team — currently ranked 8th (bottom of active backlog).

### Leadership Asks

Dedicated test environment approval request submitted to Infrastructure team (pending)

CI/CD pipeline task prioritisation request submitted to DevOps lead

### Delayed Tasks

CI/CD test automation pipeline configuration (ongoing — DevOps backlog item).

### Summary

A strong foundational month. The testing infrastructure is in place and early coverage is building on a solid base. The main systemic issues to resolve in March are the shared environment and CI/CD pipeline, both of which will compound in impact as the team grows its automation suite.

## Actions and Decisions Required for March

| # | Action / Decision | Owner | Due | Priority |
| --- | --- | --- | --- | --- |
| 1 | Escalate Salesforce sandbox provisioning to vendor account executive if not resolved by March 7 | Sponsor / David Reyes | March 7 | Critical |
| 2 | Establish DBA schema review SLA (target: 48 hours) | PMO / DBA Manager | March 7 | High |
| 3 | Approve dedicated test environment (Azure, ~$340/month) | Finance / Sponsor | March 14 | High |
| 4 | Make IE11 browser support decision | IT Director | March 14 | High |
| 5 | Make real-time vs. batch CRM sync decision | Architecture / Sponsor | March 7 | High |
| 6 | Provision dedicated staging environment | Infrastructure Team | March 21 | High |
| 7 | Configure CI/CD test automation pipeline | DevOps Team | March 28 | Medium |
| 8 | Approve additional Backend Dev resource for Q2 (pending formal request) | HR / Finance | March 21 | Medium |

March completion target: 58% overall project completion

Next monthly report due: April 3, 2026